## Summary
Project: |  | WINU TAILINGS STORAGE FACILITY DESIGN |  |  |  |  | Company: |  | WWL AUSTRALIA PTY LTD
Contract: B013 | [6 empty] | PO: |  | 3104089793
Budget - Current situation | [6 empty] | Date: |  | 2020-09-11
Progress Claim
| Task | Description | Current Budget |  |  | Previous Accum (Aug) |  |  |  | Current |  |  | Accumulate
|  |  | UoM | Planned Value | Total (A$) | UoM | Amount (A$) | % |  | UoM | Amount (A$) | % | UoM | Amount (A$) | %
| 1 | Conceptual Study - Project initiation | Glb | 24770 | 24770 | Glb | 7485 | 30.22% |  | Glb | 0 | 0% | Glb | 7485 | 30.22%
| 2 | Conceptual Study - Review of Preliminary Study | Glb | 28744 | 28744 | Glb | 93509.75 | 325.3% |  | Glb | 0 | 0% | Glb | 93509.75 | 325.3%
| 3 | Conceptual Study - TSF Expansion to 100Mt | Glb | 62574 | 62574 | Glb | 112306.25 | 179.5% |  | Glb | 0 | 0% | Glb | 112306.25 | 179.5%
| 4 | Conceptual Study - Report collation and presentations | Glb | 45535 | 45535 | Glb | 34143.75 | 74.98% |  | Glb | 0 | 0% | Glb | 34143.75 | 74.98%
| 5 | Conceptual Study - Liaison | Glb | 29874 | 29874 | Glb | 9995 | 33.46% |  | Glb | 0 | 0% | Glb | 9995 | 33.46%
| 6 | Conceptual Study - Project management | Glb | 32715 | 32715 | Glb | 39390 | 120.4% |  | Glb | 0 | 0% | Glb | 39390 | 120.4%
| 7 | Detailed Design - Initiation | Glb | 1865 | 1865 | Glb | 3090 | 165.7% |  | Glb | 0 | 0% | Glb | 3090 | 165.7%
| 8 | Detailed Design - Enginering analyses and design | Glb | 84021.15 | 84021.15 | Glb | 116315 | 138.4% |  | Glb | 3720 | 4.427% | Glb | 120035 | 142.9%
| 9 | Detailed Design-Drawing preparation | Glb | 70560 | 70560 | Glb | 53525 | 75.86% |  | Glb | 3740 | 5.3% | Glb | 57265 | 81.16%
| 10 | Detailed Design - Construction Contract documentation | Glb | 63325 | 63325 | Glb | 25940 | 40.96% |  | Glb | 0 | 0% | Glb | 25940 | 40.96%
| 11 | Detailed Design - Draft Reports and Manuals | Glb | 27020 | 27020 | Glb | 5940 | 21.98% |  | Glb | 0 | 0% | Glb | 5940 | 21.98%
| 12 | Detailed Design- Finalised reports and manuals | Glb | 8350 | 8350 | Glb | 3040 | 36.41% |  | Glb | 0 | 0% | Glb | 3040 | 36.41%
| 13 | Detailed Design - Liason workshops and presentations | Glb | 70015 | 70015 | Glb | 22645 | 32.34% |  | Glb | 0 | 0% | Glb | 22645 | 32.34%
| 14 | Detailed Design-Project management | Glb | 35274.5 | 35274.5 | Glb | 35255 | 99.94% |  | Glb | 4065 | 11.52% | Glb | 39320 | 111.5%
[5 empty] | 584642.65 |  | 562579.75 |  |  |  | 11525 |  |  | 574105 | 98.2%
|  |  |  | Inc CN-007 and Mark-up | 508269.65 | [5 empty] | Exceeded |  |  | -65835.35
| 15 | Change Notices (Exc CN-007) | Glb | 348395 | 348395 | Glb | 251020 | 72.05% |  | Glb | 41885 | 12.02% | Glb | 292905 | 84.07%
[5 empty] | 348395 |  | 251020 |  |  |  | 41885 |  |  | 292905 | 84.07%
|  | Accumulated |  |  | 856664.65 |  | 813599.75 |  |  |  | 53410 |  |  | 867010 | 101.2%
[11 empty] | Remaining up today |  |  | -10345.35
[11 empty] | CN for Extra PM |  |  | 10720.5
[11 empty] | Remaining |  |  | 375.15

## Change Register
WINU TAILINGS STORAGE FACILITY DESIGN
Change Register | [9 empty] | PCNs Approved | PCNs Awaiting Approval | PCNs Rejected | Total PCNs Raised
As at: | 2020-09-11 | [8 empty] | 19 | 0 | 0 | 19
0
PCN No | PCN Title | Description / Benefit | Raised by | Raised As | Estimated Hours Required | Estimated Cost Impact | Estimated Schedule Impact | Status | Approved/ Rejected Date | Total Hours Approved | Total Approved (Engineer Direct hours driven costs) $ (A) | Amount Approved (3rd party and indirect expenses) $ (B) | Total Approved PCN $ A+B | Actual Hours Required | Actual Cost Impact | Actual Schedule Impact | Comments
[5 empty] | hrs | AUD |  |  |  | hrs | AUD | AUD | AUD
001 | CHANGE NOTICE N° WWL-001 | Evaluation of Stage 2 TSF where production would be increased to 25Mtpa with a total storage of 375Mt |  |  | 201 | 32025 |  | Approved |  |  |  |  | 0
002 | CHANGE NOTICE N° WWL-002 | Conceptual design of a Stage 1 Base Case TSF to accommodate 7Mtpa over 10 years. (7Mtpa) |  |  | 69 | 13105 |  | Approved |  |  |  |  | 0
003 | CHANGE NOTICE N° WWL-003 | Trade off of length of the TSF, height of embankments and footprint with SWOT analyses for each option documented in a Memorandum.(Optimisation) |  |  | 52 | 10600 |  | Approved |  |  |  |  | 0
004 | CHANGE NOTICE N° WWL-004 | Conceptual design of a stand alone PAF tailings storage facility. |  |  | 70 | 13350 |  | Approved |  |  |  |  | 0
005 | CHANGE NOTICE N° WWL-005 | Additional materials take offs to assist with embankment construction optimisation between Ausenco and Mine Planning. (MTO) |  |  | 43 | 9855 |  | Approved |  |  |  |  | 0
006 | CHANGE NOTICE N° WWL-006 | Balance of time expended on geometric modelling of alternative TSF configurations as well as Stage 2.(Configurations) |  |  | 72 | 12120 |  | Approved |  |  |  |  | 0
007 | CHANGE NOTICE N° WWL-007 | Reduction in scope for the detailed design of the TSF return water system by AQ2, WWL's specialist sub-consultant.(Water Return AQ2) |  |  | -533 | -82895 |  | Approved |  |  |  |  | 0
008 | CHANGE NOTICE N° WWL-008 | Deformation analyses using FLAC to optimise the embankment-waste rock dump interface |  |  | 234 | 35330 |  | Approved |  |  |  |  | 0
009 | CHANGE NOTICE N° WWL-002A | Extend- Extension of the LOM capacity of the TSF at 7Mtpa production first to a storage capacity of 143Mt and then further to a capacity of 153Mt |  |  | 55 | 9595 |  | Approved |  |  |  |  | 0
010 | CHANGE NOTICE N° WWL-003A | Extend-Optimisation of the LOM TSF layout through a comparison of an expanded vs a raised TSF configuration |  |  | 60 | 10960 |  | Approved |  |  |  |  | 0
011 | CHANGE NOTICE N° WWL-004A | Extend-Optimisation of the PAF facility location and alignment within the TSF |  |  | 161 | 26965 |  | Approved |  |  |  |  | 0
012 | CHANGE NOTICE N° WWL-005A | Extend-Materials take-offs for each of the configurations evaluated (totaling 12 configuations with detailed schduling of 5 of these) |  |  | 118 | 18190 |  | Approved |  |  |  |  | 0
013 | CHANGE NOTICE N° WWL-006A | Extend-Comparison of potential measures to manage the risk of internal erosion (piping) through the external PAF embankments. - Design to enhance constructability over the dunes |  |  | 147 | 24975 |  | Approved |  |  |  |  | 0
014 | CHANGE NOTICE N° WWL-008A | Consolidation settlement analysis associated with construction of the embankments over the dunes |  |  | 158 | 25660 |  | Approved |  |  |  |  | 0
015 | CHANGE NOTICE N° WWL-009 | Probabilistic seepage analysis to establish seepage gradients at the toe of the embankments with confidence limits. Preparation of a fault-event tree to allow comparison of risks wih ANCOLD risk criteria. |  |  | 104 | 21355 |  | Approved |  |  |  |  | 0
016 | CHANGE NOTICE N° WWL-010 | Scheduling of embankment construction |  |  | 134 | 24250 |  | Approved
017 | CHANGE NOTICE N° WWL-011 | Prapare presentations for meetings |  |  | 70 | 11390 |  | Approved
018 | CHANGE NOTICE N° WWL-012 | Geotehcnical assessment for the high sulfur tailings |  |  | 244 | 34120 |  | Approved
019 | CHANGE NOTICE N° WWL-013 | Engineering support |  |  | 86 | 14550 |  | Approved
|  |  |  | Excl CN-007 | 1545 | 348395 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note: all costs and rates above are exclusive of GST.
In Scope
Out of Scope

## AQ2
Charged Winu
Feb | 2862.75
Mar | 363.75
Apr | 1527.5
May | 11367.25
Jun | 965
Jul
Aug | -485
16601.25
Invoices paid
Feb | 2772
May | 13671
Jun | 630
17073
Proposal
120432
CH-007 | 82895
AQ2 - New budget
37537